## Centre Infrastructure Checklist
Centre Infrastructure Checklist
S No | Work Description | Status | Date of completion | Remarks (if any)
All Rooms (excluding passage)
1 | False Ceiling
2 | Removal of Ceiling fans and current tubelights
3 | Installation of Ceiling lights and wall mounted fans |  |  | Proctor room fan left
4 | Refurbishment of electrical sockets
5 | Re-paint all walls post work
6 | AC outdoor units
7 | AC indoor units + water outlets
8 | CCTV wiring
9 | CCTV and NVR installation |  |  | Switches installed late; feed reorientation done on 11 June
10 | Internet + LAN installation
11 | Centre, CBT, SBT - Labelling with steel letters |  |  | Anjum to provide
Waiting Area
1 | Additional power sockets for ACs*
2 | Additional power socket for computers* |  |  | Extension cords used
3 | Refurbish all existing doors (frames and leafs)
4 | Blinders for windows
5 | Installation of LED TV and 2 PCs with software
6 | Installation of lockers
Computer Based Lab
1 | Additional power sockets for ACs*
2 | Additional power socket for TV*
3 | Enhance window sound-proofing and fit adjustable blinds
4 | Refurbish all existing doors (frames and leafs)
5 | Furniture installation
6 | Installation of LED TV, UPS, and PCs with software
Skill Based Lab
1 | Install acoustic wall panels and matching door assemblies for improved sound insulation
2 | Enhance window sound-proofing and fit adjustable blinds
3 | Install a sink at the designated skill station
4 | Refurbish all existing doors (frames and leafs)
5 | Additional sockets as required* |  |  | Extension cords
6 | Repair and re-lay damaged skirting tiles
7 | Concealing of current wirings
8 | Remaining CCTV installation (4 cameras at shoulder level at designated stations)
9 | Set-up of all 8 skill stations with furniture and equipment |  |  | Medical equipment to be cross-checked
10 | Installation and plugging of PCs at all skill stations and proctor room |  |  | Extension cords
11 | Furniture installation in proctor room
12 | LED installation in proctor room
13 | Station Door Labels
Passage
1 | Wall paint & finishing (after AC water outlet work)
2 | False ceiling
3 | CCTV wiring
4 | CCTV camera installation